## Projects
Name | Description | Owner | PM | Status | BusinessUnit | Budget Plan | Budget Actual | Budget Additional | Vendor Name | Vendor Contact | Vendor Value | Man Days Plan | Man Days Actual
Cloud Migration 2025 | Strategic initiative for Infrastructure | John Doe | PM John | Planning | Infrastructure | 100000 | 20000 | 0 | Vendor A | contact@vendorA.com | 50000 | 100 | 20
AI Customer Support | Strategic initiative for Innovation | Alice Smith | PM Alice | In Progress | Innovation | 200000 | 40000 | 0 | Vendor B | contact@vendorB.com | 100000 | 200 | 40
Enterprise Security Audit | Strategic initiative for Security | Bob Jones | PM Bob | On Hold | Security | 300000 | 60000 | 0 | Vendor C | contact@vendorC.com | 150000 | 300 | 60
Mobile App Redesign | Strategic initiative for Product | Jane Roe | PM Jane | Planning | Product | 400000 | 80000 | 0 | Vendor D | contact@vendorD.com | 200000 | 400 | 80
Data Warehouse Revamp | Strategic initiative for Data | Mike Data | PM Mike | In Progress | Data | 500000 | 100000 | 0 | Vendor E | contact@vendorE.com | 250000 | 500 | 100

## Final Products
Project Name | Description | Owner | Budget
Cloud Migration 2025 | Cloud Migration 2025 - Product 1 | John Doe | 30000
Cloud Migration 2025 | Cloud Migration 2025 - Product 2 | John Doe | 30000
AI Customer Support | AI Customer Support - Product 1 | Alice Smith | 30000
AI Customer Support | AI Customer Support - Product 2 | Alice Smith | 30000
AI Customer Support | AI Customer Support - Product 3 | Alice Smith | 30000
Enterprise Security Audit | Enterprise Security Audit - Product 1 | Bob Jones | 30000
Enterprise Security Audit | Enterprise Security Audit - Product 2 | Bob Jones | 30000
Mobile App Redesign | Mobile App Redesign - Product 1 | Jane Roe | 30000
Mobile App Redesign | Mobile App Redesign - Product 2 | Jane Roe | 30000
Mobile App Redesign | Mobile App Redesign - Product 3 | Jane Roe | 30000
Data Warehouse Revamp | Data Warehouse Revamp - Product 1 | Mike Data | 30000
Data Warehouse Revamp | Data Warehouse Revamp - Product 2 | Mike Data | 30000

## Phases
Final Product Description | Description | Owner | Budget | Timeline
Cloud Migration 2025 - Product 1 | Cloud Migration 2025 - Product 1 - Phase 1 | Lead 1 | 10000 | Q1 2025
Cloud Migration 2025 - Product 1 | Cloud Migration 2025 - Product 1 - Phase 2 | Lead 2 | 10000 | Q2 2025
Cloud Migration 2025 - Product 1 | Cloud Migration 2025 - Product 1 - Phase 3 | Lead 3 | 10000 | Q3 2025
Cloud Migration 2025 - Product 2 | Cloud Migration 2025 - Product 2 - Phase 1 | Lead 1 | 10000 | Q1 2025
Cloud Migration 2025 - Product 2 | Cloud Migration 2025 - Product 2 - Phase 2 | Lead 2 | 10000 | Q2 2025
AI Customer Support - Product 1 | AI Customer Support - Product 1 - Phase 1 | Lead 1 | 10000 | Q1 2025
AI Customer Support - Product 1 | AI Customer Support - Product 1 - Phase 2 | Lead 2 | 10000 | Q2 2025
AI Customer Support - Product 1 | AI Customer Support - Product 1 - Phase 3 | Lead 3 | 10000 | Q3 2025
AI Customer Support - Product 2 | AI Customer Support - Product 2 - Phase 1 | Lead 1 | 10000 | Q1 2025
AI Customer Support - Product 2 | AI Customer Support - Product 2 - Phase 2 | Lead 2 | 10000 | Q2 2025
AI Customer Support - Product 3 | AI Customer Support - Product 3 - Phase 1 | Lead 1 | 10000 | Q1 2025
AI Customer Support - Product 3 | AI Customer Support - Product 3 - Phase 2 | Lead 2 | 10000 | Q2 2025
AI Customer Support - Product 3 | AI Customer Support - Product 3 - Phase 3 | Lead 3 | 10000 | Q3 2025
Enterprise Security Audit - Product 1 | Enterprise Security Audit - Product 1 - Phase 1 | Lead 1 | 10000 | Q1 2025
Enterprise Security Audit - Product 1 | Enterprise Security Audit - Product 1 - Phase 2 | Lead 2 | 10000 | Q2 2025
Enterprise Security Audit - Product 1 | Enterprise Security Audit - Product 1 - Phase 3 | Lead 3 | 10000 | Q3 2025
Enterprise Security Audit - Product 2 | Enterprise Security Audit - Product 2 - Phase 1 | Lead 1 | 10000 | Q1 2025
Enterprise Security Audit - Product 2 | Enterprise Security Audit - Product 2 - Phase 2 | Lead 2 | 10000 | Q2 2025
Mobile App Redesign - Product 1 | Mobile App Redesign - Product 1 - Phase 1 | Lead 1 | 10000 | Q1 2025
Mobile App Redesign - Product 1 | Mobile App Redesign - Product 1 - Phase 2 | Lead 2 | 10000 | Q2 2025
Mobile App Redesign - Product 1 | Mobile App Redesign - Product 1 - Phase 3 | Lead 3 | 10000 | Q3 2025
Mobile App Redesign - Product 2 | Mobile App Redesign - Product 2 - Phase 1 | Lead 1 | 10000 | Q1 2025
Mobile App Redesign - Product 2 | Mobile App Redesign - Product 2 - Phase 2 | Lead 2 | 10000 | Q2 2025
Mobile App Redesign - Product 3 | Mobile App Redesign - Product 3 - Phase 1 | Lead 1 | 10000 | Q1 2025
Mobile App Redesign - Product 3 | Mobile App Redesign - Product 3 - Phase 2 | Lead 2 | 10000 | Q2 2025
Mobile App Redesign - Product 3 | Mobile App Redesign - Product 3 - Phase 3 | Lead 3 | 10000 | Q3 2025
Data Warehouse Revamp - Product 1 | Data Warehouse Revamp - Product 1 - Phase 1 | Lead 1 | 10000 | Q1 2025
Data Warehouse Revamp - Product 1 | Data Warehouse Revamp - Product 1 - Phase 2 | Lead 2 | 10000 | Q2 2025
Data Warehouse Revamp - Product 1 | Data Warehouse Revamp - Product 1 - Phase 3 | Lead 3 | 10000 | Q3 2025
Data Warehouse Revamp - Product 2 | Data Warehouse Revamp - Product 2 - Phase 1 | Lead 1 | 10000 | Q1 2025
Data Warehouse Revamp - Product 2 | Data Warehouse Revamp - Product 2 - Phase 2 | Lead 2 | 10000 | Q2 2025

## Deliverables
Phase Description | Description | Owner | Budget | Status
Cloud Migration 2025 - Product 1 - Phase 1 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Cloud Migration 2025 - Product 1 - Phase 1 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Cloud Migration 2025 - Product 1 - Phase 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Cloud Migration 2025 - Product 1 - Phase 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Cloud Migration 2025 - Product 1 - Phase 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Cloud Migration 2025 - Product 1 - Phase 3 | Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Cloud Migration 2025 - Product 2 - Phase 1 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Cloud Migration 2025 - Product 2 - Phase 1 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Cloud Migration 2025 - Product 2 - Phase 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Cloud Migration 2025 - Product 2 - Phase 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Cloud Migration 2025 - Product 2 - Phase 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
AI Customer Support - Product 1 - Phase 1 | AI Customer Support - Product 1 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
AI Customer Support - Product 1 - Phase 1 | AI Customer Support - Product 1 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
AI Customer Support - Product 1 - Phase 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
AI Customer Support - Product 1 - Phase 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
AI Customer Support - Product 1 - Phase 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
AI Customer Support - Product 1 - Phase 3 | AI Customer Support - Product 1 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
AI Customer Support - Product 2 - Phase 1 | AI Customer Support - Product 2 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
AI Customer Support - Product 2 - Phase 1 | AI Customer Support - Product 2 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
AI Customer Support - Product 2 - Phase 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
AI Customer Support - Product 2 - Phase 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
AI Customer Support - Product 2 - Phase 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
AI Customer Support - Product 3 - Phase 1 | AI Customer Support - Product 3 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
AI Customer Support - Product 3 - Phase 1 | AI Customer Support - Product 3 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
AI Customer Support - Product 3 - Phase 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
AI Customer Support - Product 3 - Phase 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
AI Customer Support - Product 3 - Phase 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
AI Customer Support - Product 3 - Phase 3 | AI Customer Support - Product 3 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 1 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 1 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Enterprise Security Audit - Product 1 - Phase 3 | Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Enterprise Security Audit - Product 2 - Phase 1 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Enterprise Security Audit - Product 2 - Phase 1 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Enterprise Security Audit - Product 2 - Phase 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Enterprise Security Audit - Product 2 - Phase 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Enterprise Security Audit - Product 2 - Phase 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 1 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 1 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 1 - Phase 3 | Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Mobile App Redesign - Product 2 - Phase 1 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 2 - Phase 1 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 2 - Phase 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 2 - Phase 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 2 - Phase 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 1 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 1 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Mobile App Redesign - Product 3 - Phase 3 | Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 1 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 1 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0
Data Warehouse Revamp - Product 1 - Phase 3 | Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 | Lead 3 | 5000 | 0
Data Warehouse Revamp - Product 2 - Phase 1 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 | Lead 1 | 5000 | 0
Data Warehouse Revamp - Product 2 - Phase 1 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 | Lead 1 | 5000 | 0
Data Warehouse Revamp - Product 2 - Phase 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 | Lead 2 | 5000 | 0
Data Warehouse Revamp - Product 2 - Phase 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 | Lead 2 | 5000 | 0
Data Warehouse Revamp - Product 2 - Phase 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 3 | Lead 2 | 5000 | 0

## Work Packages
Deliverable Description | Description | Assignee | Budget | Status
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 3 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 3 | Cloud Migration 2025 - Product 1 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 | Cloud Migration 2025 - Product 1 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 3 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 3 | Cloud Migration 2025 - Product 2 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 1 - Deliverable 1 | AI Customer Support - Product 1 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 1 - Deliverable 1 | AI Customer Support - Product 1 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 1 - Deliverable 1 | AI Customer Support - Product 1 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 1 - Phase 1 - Deliverable 2 | AI Customer Support - Product 1 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 1 - Deliverable 2 | AI Customer Support - Product 1 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 1 - Deliverable 2 | AI Customer Support - Product 1 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 1 - Phase 1 - Deliverable 2 | AI Customer Support - Product 1 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 1 - Phase 2 - Deliverable 1 | AI Customer Support - Product 1 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 2 - Deliverable 1 | AI Customer Support - Product 1 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 2 - Deliverable 1 | AI Customer Support - Product 1 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 1 - Phase 2 - Deliverable 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 2 - Deliverable 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 2 - Deliverable 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 1 - Phase 2 - Deliverable 2 | AI Customer Support - Product 1 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 1 - Phase 2 - Deliverable 3 | AI Customer Support - Product 1 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 2 - Deliverable 3 | AI Customer Support - Product 1 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 3 - Deliverable 1 | AI Customer Support - Product 1 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 1 - Phase 3 - Deliverable 1 | AI Customer Support - Product 1 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 1 - Phase 3 - Deliverable 1 | AI Customer Support - Product 1 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 2 - Phase 1 - Deliverable 1 | AI Customer Support - Product 2 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 2 - Phase 1 - Deliverable 1 | AI Customer Support - Product 2 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 2 - Phase 1 - Deliverable 1 | AI Customer Support - Product 2 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 2 - Phase 1 - Deliverable 2 | AI Customer Support - Product 2 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 2 - Phase 1 - Deliverable 2 | AI Customer Support - Product 2 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 2 - Phase 1 - Deliverable 2 | AI Customer Support - Product 2 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 2 - Phase 1 - Deliverable 2 | AI Customer Support - Product 2 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 2 - Phase 2 - Deliverable 1 | AI Customer Support - Product 2 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 2 - Phase 2 - Deliverable 1 | AI Customer Support - Product 2 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 2 - Phase 2 - Deliverable 1 | AI Customer Support - Product 2 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 2 - Phase 2 - Deliverable 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 2 - Phase 2 - Deliverable 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 2 - Phase 2 - Deliverable 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 2 - Phase 2 - Deliverable 2 | AI Customer Support - Product 2 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 2 - Phase 2 - Deliverable 3 | AI Customer Support - Product 2 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 2 - Phase 2 - Deliverable 3 | AI Customer Support - Product 2 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 1 - Deliverable 1 | AI Customer Support - Product 3 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 1 - Deliverable 1 | AI Customer Support - Product 3 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 1 - Deliverable 1 | AI Customer Support - Product 3 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 3 - Phase 1 - Deliverable 2 | AI Customer Support - Product 3 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 1 - Deliverable 2 | AI Customer Support - Product 3 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 1 - Deliverable 2 | AI Customer Support - Product 3 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 3 - Phase 1 - Deliverable 2 | AI Customer Support - Product 3 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 3 - Phase 2 - Deliverable 1 | AI Customer Support - Product 3 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 2 - Deliverable 1 | AI Customer Support - Product 3 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 2 - Deliverable 1 | AI Customer Support - Product 3 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 3 - Phase 2 - Deliverable 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 2 - Deliverable 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 2 - Deliverable 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
AI Customer Support - Product 3 - Phase 2 - Deliverable 2 | AI Customer Support - Product 3 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
AI Customer Support - Product 3 - Phase 2 - Deliverable 3 | AI Customer Support - Product 3 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 2 - Deliverable 3 | AI Customer Support - Product 3 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 3 - Deliverable 1 | AI Customer Support - Product 3 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
AI Customer Support - Product 3 - Phase 3 - Deliverable 1 | AI Customer Support - Product 3 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
AI Customer Support - Product 3 - Phase 3 - Deliverable 1 | AI Customer Support - Product 3 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 3 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 3 | Enterprise Security Audit - Product 1 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 | Enterprise Security Audit - Product 1 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 3 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 3 | Enterprise Security Audit - Product 2 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 1 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 1 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 2 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 2 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 2 - Deliverable 3 | Mobile App Redesign - Product 3 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 | Mobile App Redesign - Product 3 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 3 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 3 | Data Warehouse Revamp - Product 1 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 | Data Warehouse Revamp - Product 1 - Phase 3 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 1 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 1 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 - WP 2 | Dev 2 | 1000 | 40
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 - WP 3 | Dev 3 | 1000 | 60
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 2 - WP 4 | Dev 4 | 1000 | 80
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 3 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 3 - WP 1 | Dev 1 | 1000 | 20
Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 3 | Data Warehouse Revamp - Product 2 - Phase 2 - Deliverable 3 - WP 2 | Dev 2 | 1000 | 40

## KPIs
Entity Type | Entity Name | Entity ID | KPI Name | Target | Actual | Unit | Status
project | Cloud Migration 2025 |  | Budget Variance | 0 | 5 | % | On Track
project | AI Customer Support |  | Budget Variance | 0 | 5 | % | On Track
project | Enterprise Security Audit |  | Budget Variance | 0 | 5 | % | On Track
project | Mobile App Redesign |  | Budget Variance | 0 | 5 | % | On Track
project | Data Warehouse Revamp |  | Budget Variance | 0 | 5 | % | On Track