## KPI Examples
Entity Type | Entity ID | KPI Name | Target | Actual | Unit | Status
project | project-001 | Overall Project Completion | 100 | 75 | % | On Track
project | project-001 | Budget Utilization | 90 | 85 | % | On Track
project | project-001 | Schedule Performance Index (SPI) | 1 | 0.95 | ratio | At Risk
project | project-001 | Cost Performance Index (CPI) | 1 | 1.05 | ratio | Ahead
project | project-001 | Defect Density | 5 | 3 | defects/KLOC | Ahead
project | project-001 | Team Productivity | 80 | 85 | story points/sprint | Ahead
final_product | fp-001 | User Adoption Rate | 80 | 65 | % | At Risk
final_product | fp-001 | System Uptime | 99.9 | 99.95 | % | Ahead
final_product | fp-001 | Response Time | 2 | 1.5 | seconds | Ahead
phase | phase-001 | Phase Completion | 100 | 90 | % | On Track
phase | phase-001 | Code Coverage | 80 | 85 | % | Ahead
phase | phase-001 | Test Pass Rate | 95 | 92 | % | At Risk
deliverable | del-001 | Quality Score | 90 | 88 | % | On Track
deliverable | del-001 | Customer Satisfaction | 4.5 | 4.7 | out of 5 | Ahead
deliverable | del-001 | Bug Resolution Time | 48 | 36 | hours | Ahead
work_package | wp-001 | Task Completion Rate | 100 | 95 | % | On Track
work_package | wp-001 | Velocity | 40 | 42 | points | Ahead

## Instructions
Field | Description
Entity Type | Type of entity: project, final_product, phase, deliverable, or work_package
Entity ID | The ID of the entity this KPI belongs to (must match an existing entity in your system)
KPI Name | Name of the KPI metric (e.g., "Code Coverage", "User Adoption Rate")
Target | Target value for this KPI (numeric)
Actual | Current actual value for this KPI (numeric)
Unit | Unit of measurement (e.g., %, ratio, hours, points, defects/KLOC)
Status | Current status: "On Track", "At Risk", "Ahead", or "Behind"

## Common IT KPIs
Category | KPI Name | Typical Unit | Description
Project Management | Schedule Performance Index (SPI) | ratio | Earned Value / Planned Value. >1 = ahead, <1 = behind
Project Management | Cost Performance Index (CPI) | ratio | Earned Value / Actual Cost. >1 = under budget, <1 = over budget
Project Management | Budget Variance | % | Percentage difference between planned and actual budget
Project Management | Schedule Variance | days | Difference between planned and actual timeline
Quality | Defect Density | defects/KLOC | Number of defects per thousand lines of code
Quality | Code Coverage | % | Percentage of code covered by automated tests
Quality | Test Pass Rate | % | Percentage of tests that pass successfully
Quality | Bug Resolution Time | hours | Average time to resolve bugs
Performance | System Uptime | % | Percentage of time system is available
Performance | Response Time | seconds | Average system response time
Performance | Throughput | transactions/sec | Number of transactions processed per second
User Adoption | User Adoption Rate | % | Percentage of target users actively using the system
User Adoption | Customer Satisfaction | out of 5 | User satisfaction score
User Adoption | Net Promoter Score (NPS) | score | Likelihood of users recommending the system
Team Productivity | Velocity | story points | Story points completed per sprint
Team Productivity | Sprint Burndown | % | Work completed vs planned in sprint
Team Productivity | Team Utilization | % | Percentage of team capacity utilized